## Sheet1
Item# | TASK | Status
1 | Numbers should be right aligned, with comma if applicable and with 2 decimal numbers (for amounts) | Mag-eerror sa saving pag may comma
2 | SAP PR | possible, but will take time
Allow characters on SAP PR column (they want to enter VARIOUS PR on this column)
3 | Payment Terms
| Payment should be "dropdown list" | done on create BAC
Add textbox for Others
Add 2 or 3 liner textbox for Description of Payment Terms, label it as "Descritpion"
4 | Supporting Documents | possible, but will take time
Collapse All and Expand All feature on attached files
5 | Sourcing Strategy
| Number of bidders should be auto populated, based from tblbidtender table | done on create BAC
6 | Basis for Awarding
| Add Lowest Price Bidder on the list | possible, but will take time
Should be able to attached files per basis of awarding
Collapse All and Expand All feature on attached files
7 | Bid Evaluation
| Allow removal of vendor not based on last inserted vendor but rather based on selected Vendor | possible, but will take time
| Removal of added criteria should also be the same with removal of Vendor | possible, but will take time
Get Performance rating on E-Sourcing (tblVendors)
| Accreditation status is not editable, get value from tblVendor | to do
| Make the ff as "dropdown list" | done on create BAC
Tech Evaluation
Fully Complied
Non Compliance
Commercial Compliance
Fully Complied
Partial Complied
Non Compliance
Contract Compliance - Complied
Partial Complied
Non Compliance
Not Applicable
8 | Commercial Details
| Orientation should be Vertical not Horizontal (You can transfer list of items on top of bid evaluation, if this could help on simplifying the layout) | done on create BAC
| Total Amount should be computed, based on qty* unit cost | to do
| Layout extends too much, scroll bar no longer useful. | to do
| Numbers should be right aligned | to do
| On initial list of Vendor they should be sorted based on accreditation status and performance rating. If ranking is already set, vendor should be sorted based on ranking. | to do
9 | Savings Generated
| Change label "Amount" to "Savings Amount" | done on create BAC
Change Accumulated Cost to Accumulated Awarded Cost
Change "% from Spend" to "% from Savings"
10 | List of Approvers | pano to? E di bale wala yung ginawa natin sa approving?
On create/edit of BAC, Buyer can tick/untick approvers.
On clarification to buyer, buyer can still tick/untick approvers but only for those who did not yet approved
11 | BAC committee on admin page
| On Create New BAC committee, add column Level | pano to, admin page?
On Edit BAC committee, add column OIC. When an OIC is assigned all task assigned to the BAC committee should be transferred to the OIC.
12 | Buyer Endorsed Page
| Remove Buyer on the Status List | ???
| Change label Bac 1 to Level 1, Level 2, etc. (based on assigned level). This should also be the case for Purchasing, BAC pages. | ???
| Endorsed BAC should always appear on this page even if it is on clarify stage. Only when approved no longer appropriate for this page. | to do
13 | On Clarify
| Remarks not relected on "Remarks/Comment" column. Should be formatted as listed below: | to do
<Date/Time of clarification>: <buyer/approver who clarifies> : <message or remarks>
14 | On Approval
| Upon tick of Approved checkbox, no pop-up form displayed. Comment or remarks on pop-up form should also reflect on "Remarks/Comments" column | to do